## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Fullstack Development
INTERN NAME: | Chirag Yadav
DOCUMENT NAME: | TEST PLAN
CREATED ON: | 2024-07-17
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | Develop a web appliaction to find right job and internship
PROJECT ID | IP23 - Fullstack Development
INTERN NAME | Chirag Yadav
PROJECT MANAGER | Harshada Topale
INTRODUCTION
(Brief introduction of the test strategies, process, workflow and methodologies used for the project)
The purpose of this document is to outline the testing strategy, scope, and activities for the web application designed to help users find the right jobs and internships. The Application Under Test (AUT) will undergo thorough testing to ensure it meets functional and non-functional requirements and aligns with quality specifications.
SCOPE
IN SCOPE (Defines the features, functional or non-functional requirements of the software that will be tested)
User registration and authentication. Job and internship search functionality. Job posting and management by employers.Mobile responsiveness and cross-browser compatibility
OUT SCOPE (Defines the features, functional or non-functional requirements of the software that will NOT be tested)
Performance testing under high concurrent user loads. Security penetration testing.
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
Ensure the Application Under Test conforms to functional and non-functional requirements. Ensure the AUT meets the quality specifications defined by the client. Identify and fix bugs/issues before the application goes live.
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
Fullstack Developer
TEST METHODOLOGY
OVERVIEW (Mention the reason of adopting a particular test methodology for the project)
Waterfall Model
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
Functional Testing: Verify AUT functions as per requirements. Integration Testing: Ensure smooth interaction between integrated modules. Regression Testing: Confirm no new bugs have been introduced in the system after fixes. Usability Testing: Validate ease of use and UI/UX standards. Compatibility Testing: Test AUT across different devices and browsers.
BUG TRIAGE (Define resolution of each bug, prioritize bugs and determine a schedule for all “To Be Fixed Bugs’)
Critical Bugs: Immediate resolution and retesting before proceeding further. Major Bugs: Resolve and retest within one sprint cycle. Minor Bugs: Resolve based on priority, either in the same release or a future one. Low Priority Bugs: Fix in subsequent releases if time and resources permit.
TEST COMPLETENESS (Define the criteria that will deem your testing complete)
100% test coverage of defined requirements. Execution of all manual and automated test cases. All critical and major bugs are resolved. Remaining minor bugs documented for future releases.
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
Test Plan Document. Test Cases and Test Scenarios. Bug Report (including status and resolution details). Test Execution Summary. Final Test Report.
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
Postman
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
Operating System: Windows 11 Browsers: Latest versions of Chrome, Firefox, Safari, and Edge. Test Tools: Postman (for API testing).
ADDITIONAL COMMENTS
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
User Registration | Valid email, password, and username | 2024-09-16 | 2024-09-16 | Myself | PASSED | Ensure the password validation meets the security requirements
User Login | Registered email and valid password | 2024-09-16 | 2024-09-16 | Myself | PASSED | Check the session or JWT token creation upon successful login.
Job Search Filtering | Keywords, location, and skills in filter options | 2024-09-16 | 2024-09-16 | Myself | PASSED | Verify that the backend query handles all filter parameters accurately.
Job Application Submission | Resume and cover letter for a specific job | 2024-09-16 | 2024-09-16 | Myself | PASSED | Ensure uploaded files are stored securely and can be retrieved by recruiters.
Responsive Design on Mobile Device | Access application on a mobile browser | 2024-09-17 | 2024-09-17 | Myself | PASSED | Test responsiveness across multiple screen sizes and orientations.
Error Handling for Invalid Login Details | Incorrect email or password | 2024-09-17 | 2024-09-17 | Myself | PASSED | Test for brute-force protection mechanisms and account lockout policies.
Profile Update | Change personal details in the profile page | 2024-09-17 | 2024-09-17 | Myself | PASSED | Validate backend updates for each modified field and ensure data consistency.
Network Failure During Application | Disconnect internet while applying for a job | 2024-09-17 | 2024-09-17 | Myself | PASSED | Test for autosave capabilities to avoid loss of data in such scenarios.
Unauthorized Access to Protected Routes | Attempt to access dashboard without logging in | 2024-09-17 | 2024-09-17 | Myself | PASSED | Ensure all protected routes are inaccessible without valid authentication tokens.
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.